## Sheet1
Task | Start Date | Day to Complete
Make abstract of project | 2018-01-07 | 5
Analysis of requirement | 2018-01-11 | 10
Design main framework | 2018-01-21 | 8
Design software interface | 2018-01-29 | 12
create database | 2018-02-10 | 5
implementation of software | 2018-02-16 | 16
Testing of Software | 2018-03-04 | 10
analysis of issues | 2018-03-14 | 4
resolved issues | 2018-03-18 | 5

## Sheet2
Task | Start Date | Day to Complete
Make abstract of project | 2018-01-07 | 5
Analysis of requirement | 2018-01-11 | 10
Design main framework | 2018-01-21 | 8
Design software interface | 2018-01-29 | 12
create database | 2018-02-10 | 5
implementation of software | 2018-02-16 | 16
Testing of Software | 2018-03-04 | 10
analysis of issues | 2018-03-14 | 4
resolved issues | 2018-03-18 | 5